## Excel Sprint Project Tracker
| Sprint Project Tracker | [7 empty] | Task in Progress | [5 empty] | Task Completed
[8 empty] | 2021-10-15 |  |  |  |  | 2021-10-22 |  |  |  |  | 2021-10-29 |  |  |  |  | 2021-11-05 |  |  |  |  | 2021-11-12 |  |  |  |  | 2021-11-19
| PROJECT START DATE | 2021-10-10 |  | SCROLL TO WEEK # |  | 1
| Sprint | Priority | Start | Finish | Duration | Status | % Complete | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11 | 2021-11-12 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18 | 2021-11-19
[8 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
| Project Summary |  | 2021-10-12 | 2021-10-22 | 9 day(s)
| Sprint 1 - User Stories |  | 2021-10-12 | 2021-10-15 | 4 day(s) |  | 100%
| US0001 | High | 2021-10-12 | 2021-10-12 | 1 day(s) | Green | 100%
| US0002 | High | 2021-10-13 | 2021-10-13 | 1 day(s) | Green | 100%
| US0003 (1 & 2) | High | 2021-10-15 | 2021-10-15 | 1 day(s) | Green | 100%
| Sprint 2 - User Stories |  | 2021-10-19 | 2021-10-22 | 4 day(s) |  | 100%
| US0003 (3 & 4) | High | 2021-10-19 | 2021-10-20 | 2 day(s) | Green | 100%
| US0004 | High | 2021-10-22 | 2021-10-22 | 1 day(s) | Green | 100%
| Feature 1 | Low | 2018-09-01 | 2018-09-05 | 3 day(s) | Green | 100%
| Feature 2 | Medium | 2018-09-15 | 2018-09-23 | 5 day(s) | Yellow | 15%
| Feature 3 | Low | 2018-09-29 | 2018-10-07 | 5 day(s) | Red | 25%
Task Id |  | Description | [5 empty] | 2021-10-11: Sub Task
US0001 |  | Code to display the welcome screen.The details of the user interface such as options displaying the user interaction information.Features to accept the user input to select one of the options listed. There should be a third option to close the application | [5 empty] | 2021-10-11: 1.List files in directory, 2.File handling tools, 3.Exit - main menu 1.Add a file to the existing directory list, 2.Delete a user specified file from the existing directory list , 3.Search a user specified file from the main directory,4.Go back to the main menu
US0002 |  | The first option should return the current file names in ascending order. The root directory can be either empty or contain few files or folders in it
US0003 |  | The second option should return the details of the user interface such as options displaying the following: 1) Add a file to the existing directory list (You can ignore the case sensitivity of the file names ) 2) Delete a user specified file from the existing directory list *You can add the case sensitivity on the file name in order to ensure that the right file is deleted from the directory list *Return a message if FNF (File not found) 3) Search a user specified file from the main directory *You can add the case sensitivity on the file name to retrieve the correct file *Display the result upon successful operation *Display the result upon unsuccessful operation 4) Option to navigate back to the main context
US0004 |  | Create Project and repository in Git Link to repository: https://github.com/git-intel/Java_LockedMe_Repo
US0005 |  | the screenshots of the output, Document Core concepts used in the project in project details

## Sprint Tracker Instructions
Excel Sprint Project Tracker - Guidance and Tips:
Type your own feature or task names and dates for each Sprint inside the table on the Excel Sprint Project Tracker sheet. The template's functions will automatically calculate the duration of each task and estimate how much each sprint will take to accomplish your goals.
The Gantt chart to the right of the Sprint Project tracker will auto-update whenever you change your tasks' dates or % Complete, or when you enter more items in the table.
To display a different time period on the timeline, change the numer next to SCROLL TO WEEK in the table.
To enter additional features or tasks, simply insert new rows within the table and type in your data.
The Excel Sprint Project Tracker lets you quickly add extra Sprints, complete with the functions that automate calculations and graphic updates. To do so, select and copy all rows correspoding to an existing Sprint section, right-click on the row where you want to include your new section, and then select Insert Copied Cells from the pop-up. Then, just replace the duplicated data with new information.
The color of the Gantt chart task bars can also be changed, by using Conditional Formatting. Select all cells corresponding to the Gantt chart, click the Conditional Formatting button on the Home tab, and then select Manage Rules. Here, choose the formula you wish to customize (Blue for Completed Tasks, Orange for Tasks in Progress), and then click on Edit Rule. This is where you'll find all customization options for the task bar formulas, including the option to change the Orange or Blue Fill color.
Changing Task Colors